## Sheet1
VIZOP
ALARM RATIONALIZATION		FEATURE DEVELOPMENT TRACKER

#	Scope	Feature	Status	Notes
	PHA model	Create listbox option that user can select to create PHA model	Debugging	Next step: code GetFullRedrawData() in class ARObjectInCore
	PHA model	VizopTalks messages	Not started
	Alarm list viewport	Create basic setup	In progress	Method SetupDisplay of class AlarmList. Using a 6-sizer design for GUI, see spec 13.
				Currently working on: populating sizers; need to start populating alarm display grid. Need to figure out how many columns and rows to show.
				Considering: make a table to contain all columns of alarm data; copy relevant columns to the grid's data table according to which columns are currently displayed.
	GetFullRedrawData() in class ARObjectInCore:	Write spec for XML message to be generated by this function	Done	Spec “Alarm list – internal XML message structure”, level 4
		Code GetFullRedrawData()	WIP
	Alarm import	Code import function	Done, to test	Method DoImport

	Alarm list export	Code export function	Not started
		Code GUI	Not designed

	Rationalize one alarm viewport	Design	Some work done in spec
		Code GUI	Not started